## All Tasks
WEEK 7 PROJECT TRACKER — ShadowDarklings ¦ Due: End of Week 7 ¦ Tag: week7-final
PART 1 — Group: Contracts Revision for OAuth (2 marks)
Task ID | Task | Owner | Status | Files / Deliverables | Notes
1.1 | Planning session — revise CONTRACTS.md for OAuth | Charles (lead), all | Not Started | CONTRACTS.md | LLM-assisted; all roles participate
1.2 | Specify /login/github route (inputs/outputs) | Charles + Megan | Not Started | CONTRACTS.md
1.3 | Specify /auth/github/callback route (inputs/outputs) | Charles + Megan | Not Started | CONTRACTS.md
1.4 | Specify required user-info fields from GitHub + missing-field handling | Megan | Not Started | CONTRACTS.md | What to do if a field is missing
1.5 | Specify local user record shape after first OAuth login | Mario | Not Started | CONTRACTS.md | New oauth_identity table
1.6 | Specify link between local user and external identity | Mario | Not Started | CONTRACTS.md | One user → multiple OAuth identities
1.7 | Specify session state after successful callback | Mario | Not Started | CONTRACTS.md | Session dict contents + cookies set
1.8 | Specify logout behavior (cleared locally vs. at provider) | Charles + Megan | Not Started | CONTRACTS.md
1.9 | Add external_dependency: github.com disclosure | Charles | Not Started | CONTRACTS.md | Cannot contract GitHub's actual behavior
1.10 | Write/update coord_session.md | Charles | Not Started | coord_session.md | Must show real cross-role engagement
PART 2 — Individual: Role Work + Playwright Test (5 marks)
Charles — Coordinator + Client-side
Task ID | Task | Owner | Status | Files / Deliverables | Notes
2C.1 | Set up GitHub OAuth app credentials in team's GitHub org | Charles | Not Started | GitHub Settings | Coordinator task
2C.2 | Document credential location in .env.example | Charles | Not Started | .env.example | Never commit .env
2C.3 | Set up test-login backdoor route /test/login/<username> | Charles | Not Started | app.py | Only active when TESTING=True
2C.4 | Set up tests/e2e/conftest.py (TESTING=True, live server) | Charles | Not Started | tests/e2e/conftest.py | SQLite test DB in /tmp
2C.5 | Maintain integration log — track contract breakages | Charles | Not Started | Ongoing | Coordinator responsibility
2C.6 | Add 'Sign in with GitHub' button on login page | Charles | Not Started | templates/login.html | Keep password form alongside
2C.7 | Post-login UX — deliberate landing page after OAuth | Charles | Not Started | Templates / JS | Not accidental
2C.8 | 'Remember me' toggle wired to session lifetime config | Charles | Not Started | templates/login.html, app.py
2C.9 | Logout button that clears state, lands on sensible page | Charles | Not Started | templates/base.html
2C.10 | Playwright test: smoke test — app starts, login loads, GitHub button present | Charles | Not Started | tests/e2e/test_coordinator_smoke.py | Cheapest possible canary
2C.11 | Write role_work.md | Charles | Not Started | role_work.md | Files touched + test description
Megan — Server-side
Task ID | Task | Owner | Status | Files / Deliverables | Notes
2M.1 | Install + wire up Authlib with GitHub provider | Megan | Not Started | app.py, requirements.txt
2M.2 | Implement /login/github — initiates OAuth flow | Megan | Not Started | app.py | authorize_redirect
2M.3 | Implement /auth/github/callback — handles GitHub return | Megan | Not Started | app.py
2M.4 | Create-or-link logic: new user vs returning vs existing+GitHub | Megan | Not Started | app.py
2M.5 | Handle missing/null provider fields → sensible defaults | Megan | Not Started | app.py | Never crash on partial payload
2M.6 | Load .env via python-dotenv — load_dotenv() before os.environ | Megan | Not Started | app.py | Must come before any env lookups
2M.7 | Use os.environ['KEY'] (bracket, not .get) for secrets | Megan | Not Started | app.py | Missing secret → crash on startup
2M.8 | Add authlib, python-dotenv to requirements.txt | Megan | Not Started | requirements.txt
2M.9 | Playwright test: happy-path login → 'Logged in as <username>' visible | Megan | Not Started | tests/e2e/test_server_login.py | Uses test-login backdoor
2M.10 | Write role_work.md | Megan | Not Started | role_work.md | Files touched + test description
Mario — DB & Security
Task ID | Task | Owner | Status | Files / Deliverables | Notes
2D.1 | Add oauth_identity table linking external provider IDs to local users | Mario | Not Started | app.py (models) | New SQLModel model
2D.2 | Migration script or clean schema update commit | Mario | Not Started | app.py or migration file
2D.3 | Set cookie flags: SECURE, HTTPONLY, SAMESITE='Lax' | Mario | Not Started | app.py (config) | Session hardening
2D.4 | Configure PERMANENT_SESSION_LIFETIME | Mario | Not Started | app.py
2D.5 | Wire 'remember me' cookie via Flask-Login | Mario | Not Started | app.py
2D.6 | Wire Flask-WTF CSRF protection to every state-changing form | Mario | Not Started | app.py, all form templates
2D.7 | Add flask-wtf to requirements.txt | Mario | Not Started | requirements.txt
2D.8 | Add playwright to requirements.txt | Mario | Not Started | requirements.txt
2D.9 | Playwright test: protected page inaccessible → accessible after login → inaccessible after logout | Mario | Not Started | tests/e2e/test_security_access.py | Verified through rendered DOM
2D.10 | Write role_work.md | Mario | Not Started | role_work.md | Files touched + test description
PART 3 — Group: Full-System Playwright Suite + Team Walkthrough (3 marks)
Task ID | Task | Owner | Status | Files / Deliverables | Notes
3.1 | First-time OAuth login — new user via backdoor → post-login page → oauth_identity row exists | All | Not Started | tests/e2e/test_full_lifecycle.py
3.2 | Returning OAuth login — same user logs out, logs back in → existing row reused, not duplicated | All | Not Started | tests/e2e/test_full_lifecycle.py
3.3 | CSRF protection works — POST without token → rejected | All | Not Started | tests/e2e/test_full_lifecycle.py | Use Playwright request context
3.4 | Session expires — short PERMANENT_SESSION_LIFETIME → protected page inaccessible | All | Not Started | tests/e2e/test_full_lifecycle.py | Time controls or sleep
3.5 | Write team_walkthrough.md — one section per test | All | Not Started | team_walkthrough.md | Behavior + regression caught per test
3.6 | Write gaps section in walkthrough | All | Not Started | team_walkthrough.md | 'We don't test X because Y'
3.7 | Ensure walkthrough reads as coherent narrative | All | Not Started | team_walkthrough.md | New teammate understands in 10 min
SHARED / INFRASTRUCTURE
Task ID | Task | Owner | Status | Files / Deliverables | Notes
S.1 | Update .env.example with OAUTH_CLIENT_ID, OAUTH_CLIENT_SECRET | Charles | Not Started | .env.example
S.2 | Ensure .env is in .gitignore | Charles | Done | .gitignore | Already in place
S.3 | Create tests/e2e/ directory | Charles | Not Started | tests/e2e/
S.4 | Create tests/e2e/conftest.py | Charles | Not Started | tests/e2e/conftest.py | TESTING=True, SQLite, live server
S.5 | Fix duplicate /api/random-tables route in app.py (L620 vs L683) | Megan | Not Started | app.py | Will cause Flask conflict
S.6 | Add authlib, playwright, flask-wtf, python-dotenv to requirements.txt | Shared | Not Started | requirements.txt | Consider batching to avoid merge conflicts
S.7 | Tag final commit week7-final | Charles | Not Started | Git | Last step

## Submission Checklist
SUBMISSION CHECKLIST
# | Deliverable | Location | Status
1 | CONTRACTS.md — updated for OAuth | Repo root | Done
2 | coord_session.md — planning session | Repo root | Done
3 | role_work.md — Charles | Repo root | Not Started
4 | role_work.md — Megan | Repo root | Not Started
5 | role_work.md — Mario | Repo root | Done
6 | team_walkthrough.md | Repo root | Not Started
7 | tests/e2e/test_full_lifecycle.py (4 scenarios) | tests/e2e/ | Not Started
8 | Individual Playwright tests (3 files) | tests/e2e/ | In Progress
9 | .env.example — updated with OAuth vars | Repo root | Not Started
10 | requirements.txt — authlib, playwright, flask-wtf, python-dotenv | Repo root | Done
11 | Git tag: week7-final | Git | Not Started
12 | Known gaps documented honestly in .md files | Various | In Progress

## Per-Person View
Charles — 19 tasks
Task ID | Task | Part | Status | Files
1.1 | Planning session — revise CONTRACTS.md | Part 1 | Not Started | CONTRACTS.md
1.2 | Specify /login/github route | Part 1 | Not Started | CONTRACTS.md
1.3 | Specify /auth/github/callback route | Part 1 | Not Started | CONTRACTS.md
1.8 | Specify logout behavior | Part 1 | Not Started | CONTRACTS.md
1.9 | Add external_dependency disclosure | Part 1 | Not Started | CONTRACTS.md
1.10 | Write coord_session.md | Part 1 | Not Started | coord_session.md
2C.1 | Set up GitHub OAuth app credentials | Part 2 | Not Started | GitHub Settings
2C.2 | Document credential location in .env.example | Part 2 | Not Started | .env.example
2C.3 | Set up test-login backdoor route | Part 2 | Not Started | app.py
2C.4 | Set up tests/e2e/conftest.py | Part 2 | Not Started | tests/e2e/conftest.py
2C.5 | Maintain integration log | Part 2 | Not Started | Ongoing
2C.6 | Add 'Sign in with GitHub' button | Part 2 | Not Started | templates/login.html
2C.7 | Post-login UX — deliberate landing page | Part 2 | Not Started | Templates / JS
2C.8 | 'Remember me' toggle | Part 2 | Not Started | login.html, app.py
2C.9 | Logout button clears state | Part 2 | Not Started | templates/base.html
2C.10 | Playwright smoke test | Part 2 | Not Started | test_coordinator_smoke.py
2C.11 | Write role_work.md | Part 2 | Not Started | role_work.md
S.1 | Update .env.example with OAuth vars | Infra | Not Started | .env.example
S.7 | Tag final commit week7-final | Infra | Not Started | Git
Megan — 15 tasks
Task ID | Task | Part | Status | Files
1.2 | Specify /login/github route | Part 1 | Not Started | CONTRACTS.md
1.3 | Specify /auth/github/callback route | Part 1 | Not Started | CONTRACTS.md
1.4 | Specify required user-info fields + missing-field handling | Part 1 | Not Started | CONTRACTS.md
1.8 | Specify logout behavior | Part 1 | Not Started | CONTRACTS.md
2M.1 | Install + wire up Authlib with GitHub provider | Part 2 | Not Started | app.py, requirements.txt
2M.2 | Implement /login/github | Part 2 | Not Started | app.py
2M.3 | Implement /auth/github/callback | Part 2 | Not Started | app.py
2M.4 | Create-or-link logic | Part 2 | Not Started | app.py
2M.5 | Handle missing/null provider fields | Part 2 | Not Started | app.py
2M.6 | Load .env via python-dotenv | Part 2 | Not Started | app.py
2M.7 | Use os.environ['KEY'] for secrets | Part 2 | Not Started | app.py
2M.8 | Add authlib, python-dotenv to requirements.txt | Part 2 | Not Started | requirements.txt
2M.9 | Playwright happy-path login test | Part 2 | Not Started | test_server_login.py
2M.10 | Write role_work.md | Part 2 | Not Started | role_work.md
S.5 | Fix duplicate /api/random-tables route | Infra | Not Started | app.py
Mario — 13 tasks
Task ID | Task | Part | Status | Files
1.5 | Specify local user record shape after OAuth login | Part 1 | Not Started | CONTRACTS.md
1.6 | Specify user ↔ external identity link | Part 1 | Not Started | CONTRACTS.md
1.7 | Specify session state after callback | Part 1 | Not Started | CONTRACTS.md
2D.1 | Add oauth_identity table | Part 2 | Not Started | app.py (models)
2D.2 | Migration script or schema update | Part 2 | Not Started | app.py
2D.3 | Set cookie flags: SECURE, HTTPONLY, SAMESITE | Part 2 | Not Started | app.py (config)
2D.4 | Configure PERMANENT_SESSION_LIFETIME | Part 2 | Not Started | app.py
2D.5 | Wire 'remember me' cookie via Flask-Login | Part 2 | Not Started | app.py
2D.6 | Wire Flask-WTF CSRF to all state-changing forms | Part 2 | Not Started | app.py, templates
2D.7 | Add flask-wtf to requirements.txt | Part 2 | Not Started | requirements.txt
2D.8 | Add playwright to requirements.txt | Part 2 | Not Started | requirements.txt
2D.9 | Playwright access-control test | Part 2 | Not Started | test_security_access.py
2D.10 | Write role_work.md | Part 2 | Not Started | role_work.md